## Sheet1
Row Labels | Count of TASK | Row Labels | Count of TASK
Bank | 4 | Completed | 13
Bank/NPST | 1 | In Progress | 6
BOM/NPST | 1 | Pending | 26
DBD | 7 | (blank) | 13
DBD/IT-Projects/FI/NPST | 1 | Grand Total | 58
DBD/Legal/NPCI | 1
DBD/NPCI | 4
DBD/NPST | 7
DCRD | 1
DCRD/DBD/NPST | 1
DCRD/FM&A | 1
NPCI/Bank/NPST | 1
NPST | 17
NPST/ NPCI | 1
ORMC committee | 1
(blank) | 9
Grand Total | 58

## PROJECT PLAN - PHASE 1
Project Plan, Bharat Bill Payment System(Phase-1)
COMPANY NAME: Bank Of Maharshtra |  |  |  | PROJECT PHASE 1 START: | 2025-08-25
Solution provider: NPST |  |  |  | TODAY: | 2025-09-29
PROJECT MANAGER: Sumeet Kumar |  |  |  | DISPLAY WEEK: | 1
S.NO. | TASK | Ownership | ACTUAL START | ACTUAL END | PLANNED START | PLANNED END | Actual End | Status | DAYS | Remarks
1 | Requirement Gathering for COU & Channel Integration & BOU |  |  |  | 2025-08-25 | 2025-09-25 | 2025-09-25 |  | 32
1.1 | Stakeholder discussions and review of MOMs, RFP, proposal, and PO. | DBD/NPST | 2025-08-25 | 2025-08-31 | 2025-08-25 | 2025-08-26 | 2025-08-26 | Completed | 2
1.2 | Requirement Gathering for COU - MB Channel | DBD/NPST | 2025-09-08 | 2025-09-09 | 2025-09-08 | 2025-09-09 | 2025-09-09 | Completed | 2
1.3 | Requirement Gathering for COU - BC Channel | DBD/IT-Projects/FI/NPST | 2025-09-10 |  | 2025-09-15 | 2025-09-24 |  | In Progress | 10 | API document & BRD document shared to FI team & IT project. API & BRD under review by them. ETA- 24.09.2025
1.4 | Requirement Gathering for BOU - Loan Management System (LMS) | BOM/NPST | 2025-09-17 | 2025-09-17 | 2025-09-17 | 2025-09-17 | 2025-09-17 | Completed | 1
1.5 | PRD Preparation and internal review with Channel Integration - MB | NPST | 2025-09-09 | 2025-09-17 | 2025-09-09 | 2025-09-17 | 2025-09-17 | Completed | 9
1.6 | PRD Preparation and internal review with BOU | NPST | 2025-09-17 |  | 2025-09-17 | 2025-09-25 | 2025-09-25 | Completed | 9 | Discussion completed for integration of Loan Repaymnet as Biller -BOU on 18.09.2025. BRD ETA -25.09.2025
1.7 | PRD Bank Review and Signoff for COU -MB channel | DBD | 2025-09-09 |  | 2025-09-18 | 2025-09-18 | 2025-09-18 | Completed | 1
1.8 | PRD Bank Review and Signoff for BOU | DBD | 2025-09-09 |  | 2025-09-26 | 2025-09-29 |  | In Progress | 4
2 | Environment Setup for COU & BOU |  |  |  | 2025-08-25 | 2025-09-29 | 2025-09-15 |  | 36
2.1 | Infra Requirement share with bank | NPST | 2025-08-28 | 2025-08-29 | 2025-08-25 | 2025-08-25 | 2025-08-25 | Completed | 1
2.2 | UAT Environment Setup | DBD/NPST | 2025-08-29 | 2025-09-09 | 2025-08-29 | 2025-09-09 | 2025-09-09 | Completed | 12
2.3 | Meeting with NPCI to discuss on the process for NBBL onboarding for BBPS | DBD/NPCI |  |  | 2025-09-10 | 2025-09-10 | 2025-09-10 | Completed | 1
2.4 | Certification with NBBL - a) Acknowledgment from RBI | DBD |  |  | 2025-09-15 | 2025-09-15 | 2025-09-15 | Completed | 1
2.5 | Bipartite Agreement between Bank and NPCI for BBPS | DBD/Legal/NPCI |  |  | 2025-09-12 | 2025-09-26 |  | In Progress |  | 1. Mail sent for Vetting on 12.09.2025. 2. Vetting on Bipartite agreement with Bank and NPCI done by legal team on 20.09.2025. 3. Send for review to NPCI on 22.09.2025
2.6 | Submission of other Documents to NPCI for NBBL onboarding | DBD/NPCI |  |  | 2025-09-15 | 2025-09-26 |  | In Progress |  | There are changes in one document- Letter of Authority. NPCI will share modified Letter of authority. ETA- 23.09.2025
2.7 | UAT NBBL Connectivity | Bank |  |  | 2025-09-25 | 2025-09-29 |  | Pending | 5 | Once the agreement between Bank and NPCI is executed, NPCI will initiate for NBBL connectivity
3 | BBPS Core Application Development (COU ) |  |  |  | 2025-09-09 | 2025-10-01 |  |  | 23
3.1 | Development - Backend | NPST | 2025-09-09 | 2025-09-19 | 2025-09-09 | 2025-09-19 | 2025-09-19 | Completed | 11
3.2 | Development - Front end | NPST | 2025-09-18 | 2025-09-24 | 2025-09-18 | 2025-09-26 | 2025-09-26 | Completed | 9 | ETA- 24.09.2025
3.3 | Unit Testing | NPST |  |  | 2025-09-20 | 2025-09-20 | 2025-09-20 | Completed | 1
3.4 | Load Testing | NPST |  |  | 2025-09-21 | 2025-10-01 |  | Pending | 11 | Dependent on NPCI UAT environment
3.5 | UAT Deployment | NPST |  |  | 2025-09-09 | 2025-09-19 | 2025-09-19 | Completed | 11
4 | BBPS Core Application Development (BOU ) |  |  |  | 2025-09-26 | 2025-10-11 |  |  | 16
4.1 | Development - Backend | NPST |  |  | 2025-09-26 | 2025-10-05 |  | Pending | 10
4.2 | Unit Testing | NPST |  |  | 2025-10-06 | 2025-10-07 |  | Pending | 2
4.3 | Load Testing | NPST |  |  | 2025-10-08 | 2025-10-10 |  | Pending | 3
4.4 | UAT Deployment | NPST |  |  | 2025-10-11 | 2025-10-11 |  | Pending | 1
5 | Approval from ORMC & NPC |  |  |  | 2025-09-22 | 2025-10-03 |  |  | 12
5.1 | Note preparedeness for approval from NPC and ORMC on BBPS | DBD |  |  | 2025-09-22 | 2025-09-25 |  | In Progress | 4
5.2 | Approval from ORMC & NPC | ORMC committee |  |  | 2025-09-24 | 2025-09-29 |  | Pending | 6
5.3 | Mail communication to DCRD - for BBPS Pool and settlement account creation | DBD |  |  | 2025-09-22 | 2025-09-22 | 2025-09-22 | Completed | 1
5.4 | Creation of BBPS pool and Settlement account | DCRD/FM&A |  |  | 2025-09-23 | 2025-10-03 |  | Pending | 11
6 | BBPS COU Certification & Integration with Channel |  |  |  | 2025-09-30 | 2025-10-17 |  |  | 18
6.1 | Onboarding on NBBL | DBD/NPCI |  |  | 2025-09-30 | 2025-10-03 |  | Pending | 4
6.2 | Certification with NBBL | NPST |  |  | 2025-10-04 | 2025-10-17 |  | Pending | 14
6.3 | Integration - MB channel | DBD/NPST |  |  | 2025-10-01 | 2025-10-03 |  | Pending | 3
6.4 | Integration with CBS | DBD/NPST |  |  | 2025-10-04 | 2025-10-08 |  | Pending | 5
6.5 | Sanity test with banking channels/CBS | DBD/NPST |  |  | 2025-10-09 | 2025-10-11 |  | Pending | 3
7 | BBPS BOU Certification |  |  |  | 2025-10-10 | 2025-10-24 |  |  | 15
7.1 | BOU onboarding on NBBL | DBD/NPCI |  |  | 2025-10-10 | 2025-10-11 |  | Pending | 2
7.2 | BOU Certification with NBBL | NPST/ NPCI |  |  | 2025-10-12 | 2025-10-16 |  | Pending | 5
7.3 | Prereqsite for Biller (Loan Managemnet System) | NPST |  |  | 2025-10-17 | 2025-10-18 |  | Pending | 2
7.4 | Integration with biller (LMS) | NPST |  |  | 2025-10-19 | 2025-10-20 |  | Pending | 2
7.5 | Integtration with CBS | Bank/NPST |  |  | 2025-10-21 | 2025-10-23 |  | Pending | 3
7.6 | Sanity Test with Biller | NPCI/Bank/NPST |  |  | 2025-10-24 | 2025-10-24 |  | Pending | 1
8 | QA |  |  |  | 2025-10-25 | 2025-10-31 |  |  | 7
8.1 | UAT Cycle 1 | NPST |  |  | 2025-10-25 | 2025-10-27 |  | Pending | 3
8.2 | UAT Cycle2 with bug fixes | DBD/NPST |  |  | 2025-10-28 | 2025-10-31 |  | Pending | 4
8.3 | UAT Sign off | DBD |  |  | 2025-10-31 | 2025-10-31 |  | Pending | 1
9 | Recon System Implementation |  |  |  | 2025-09-19 | 2025-09-30 |  |  | 12
9.1 | Recon Requirement gathering & PRD Preparation | NPST |  |  | 2025-09-19 | 2025-09-26 |  | In Progress | 8
9.2 | Bank PRD Review and Finalization | DBD |  |  | 2025-09-28 | 2025-09-30 |  | Pending | 3
9.3 | Bank Review and Sign off | DBD/DCRD |  |  | 2025-09-30 | 2025-09-30 |  | Pending | 1
9.4 | Technical Discussion with DCRD for reconciliation | DCRD/DBD/NPST |  |  | 2025-09-30 | 2025-09-30 |  | Pending | 1
9.5 | Integration of BBPS with Recon System | DCRD |  |  | 2025-10-02 | 2025-10-15 |  | Pending | 14
10 | Infra Setup - Production | Bank |  |  | 2025-09-26 | 2025-10-01 |  | Pending | 6
11 | Audit & Compliance (Hardware & Software) | Bank |  |  | 2025-10-31 | 2025-11-12 |  | Pending | 13
12 | Go Live Activities | Bank |  |  | 2025-11-15 | 2025-11-20 |  | Pending | 6
Insert new rows ABOVE this one
| R |  |  |  | R | R |  | R | R
Formulas:
PLANNED START = MIN([PLANNED START, row below]:F16)
PLANNED START = [PLANNED END, row above]+1
PLANNED END = MAX([PLANNED END, row below]:G16)
PLANNED END = WORKDAY([PLANNED START],1)
Actual End = MAX([Actual End, row below]:H16)
Actual End = WORKDAY([PLANNED END],0)
Note on J8: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.